## Issue Log
ISSUE MANAGEMENT LOG
Project Name: |  |  | Indoor Drone R&D
Project Manager Name: |  |  | Tran Duc Huy
ID | Status | Priority | Issue Description | Owner | Escalation Needed (Y/N)? | Impact | Actions | Logged By | Final Resolution & Follow-on actions | NOTE
ST001 | Closed | High | Web UI fail to send commands to Tello |  | No | Fail to manual control and sending commands to Tello | Research about json post method |  | Change the queries Method from ['GET'] to ['POST']
ST002 | Closed | Critical | Video data received but does not display |  | Yes | Fail to implement computer vision | Research about Video streaming functions and decoding video datas |  | Integrate a library to decode incomming video datas
ST003 | Closed | Medium | Video data received but does not display onto the web, instead open a new window. |  | Yes | Fail to control Tello via UI | Find a way to pipe video stream onto the UI |  | Combine FFMPEG extension into the web backend to stream video
ST004 | Closed | Medium | FFMPEG failed to boot |  | No | Fail to control Tello via UI | Learn more about FFMPEG extension |  | Install FFMPEG path, modified video received and decoded.
ST005 | Work In Progress | Low | Patrol mode does not execute per command sent |  | No | Impact test results and futher development | Automated flight required an ideal environment |  | Create an ideal environment for drone to fly
ST006 | Closed | Critical | Total failure of integration computer vison to inact facial recognition |  | Yes | Unable to engage with automated flight | Understand how OpenCV works |  | Lower video resolution
ST007 | Work In Progress | Low | Drone failed to center around faces because the commands sent from ground control does not reach the drone |  | No | No impact | Rework on the backend |  | Rework the backend and optimize data rates
ST008 | Open | Low | Drone return "invalid IMU" while operating with facial recognition |  | No | No impact
ST009 | Work In Progress | Medium | Threading problem while operate in face traking mode |  | Yes | Multiple commands will cause drone to behave crazy | Rework threading codes |  | Create Singleton class to simplify commands sent and fix threading
ST010 | Work In Progress | Medium | Face detected and follow up commands are sent but Drone fail to execute the commands |  | Yes | Future integration of smart flying might run into trouble | Work out on why the commands does not activated |  | Basic automation commands such as "forward(0.3)" are not reliable. Creating a new set of commands to execute automation flgith
SV001 | Closed | Medium | SITL failure |  | No | Unable to test the script | Fix PATH |  | Need to correct <bashrc> file as well as note it down on USER GUIDE
SV002 | Closed | Critical | Inputing movement command by using SITL terminal |  | Yes | Future scripting will meet a halt | "Find out reason and resolve it" - PM |  | STABILIZE mode does not accept console commands
SV003 | Closed | High | "APM: PreArm: Check mag field" error poping up while executing scripted mission |  | No | Affecting project scope | Research about the error codes and create solution to it |  | PreFlight parameters need to be calibrated before command drone to follow missons
SV004 | Work In Progress | High | Non-GPS flying is not available with most ArduPilot Drone. Even with SITL drones |  | Yes | Indoor flying will have inaccurate results and mess up navigation | Bypass GPS requirement in drone flying |  | Create a sample code with GUIDED_NO_GPS (Need further research)
HV001 | Open | Medium | RC controller need to be present to arm the Drone |  | Yes | Can not effectively control the drone or its movement without understanding its telemetry
HV002 | Open | Low | GPS module is required even for Indoor drone. |  | No | Affecting project scope
Note on A4: A unique ID number Check Appendix
Note on B4: Status: - Open: The issue is currently open but has not yet been addressed. - Work In Progress: The issue is being actively worked to develop a resolution. - Closed: The issue is no longer considered an active project threat and can be closed with or without resolution.
Note on C4: Critical, High, Medium, Low. Critical: Issue will stop project progress. High: Issue will likely impact budget, schedule or scope. Medium: Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope. Low: Issue is low impact and/or low effort to resolve.
Note on D4: Give a brief description of the issue.
Note on E4: The individual most responsible for working towards resolving the issue.
Note on F4: “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on G4: Describe the impact of the issue. This may be in terms of the project constraints of time, cost and scope.
Note on H4: Actions to mitigate the issue, avoid the issue or resolve the issue.
Note on J4: Document the final outcome. Is the issue resolved and if so how? Are there any follow-on actions? Are there any follow-on risks?I

## Appendix
|  | IDs | Stand for
|  | S | Software
|  | H | Hardware
|  | IDs | Stand for
|  | V | Drone version 1
|  | A | Drone version 2 (ArduPilot)
|  | T | Tello
Example: ID1 + ID2 + issue
|  | ST001 | Tello software issue no.001
|  | HV001 | Drone v.1 issue no.001
Issue severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.